GRANT WRITING & POST-AWARD REPORTING

# Grant Report Template

Translate activities, results, financial performance, learning, and next steps into a credible funder report.

VERSION 1.0  •  AUGUST 2026

Built for clear decisions, defensible communication, and practical reuse.

# How to use this template

Use this structure for interim, progress, or final reports. Start with the award agreement and the funder’s current reporting form. Replace every bracketed prompt, remove non-applicable sections, and reconcile all reported figures with the approved budget, program records, and prior submissions.

Confirm the reporting period, portal fields, character limits, attachments, certification language, and deadline.

Build a commitments-to-results crosswalk using the approved proposal, logic model, work plan, and budget.

Report actual outputs and outcomes with sources, dates, units, and limitations; do not convert estimates into facts.

Explain material variance without hiding it, and connect each variance to a corrective action or approved change.

Use participant stories only with appropriate consent and without unnecessary identifying information.

Complete the financial reconciliation and final review before copying content into the funder’s portal.

|  | Report against the promise, not the memory A strong report compares what was approved with what occurred, explains the difference, and shows what the organization learned and changed. |
| --- | --- |

# Reporting brief

| Funder and program — Required | [Funder name, grant program, award or agreement number] |
| --- | --- |
| Grantee — Required | [Legal organization name] |
| Funded project — Required | [Project or program title] |
| Award and request — Required | [$ award amount; total project budget if relevant] |
| Reporting period — Required | [Start date through end date] |
| Report type — Required | [Interim / progress / final / closeout / special report] |
| Submission rules — Required | [Portal, file format, character limits, attachments, signature, and deadline] |
| Primary contacts — Required | [Program lead, finance lead, authorized signer, funder contact] |
| Approved changes — Optional | [Scope, timing, budget, target, or personnel changes and approval dates] |
| Data limitations — Required | [Known gaps, lags, sample limits, collection changes, or definitions] |

# Executive summary

During [reporting period], [organization] used [award amount / funding purpose] to [core activities] for [people, place, or system].

The strongest verified result was [outcome], evidenced by [source and value]. Against the approved plan, the project [met / exceeded / partially met] [number] of [number] priority commitments.

The most material variance was [variance]. It occurred because [cause], affected [scope or result], and was addressed through [approved adjustment or corrective action].

In the next period, the organization will [priority next step], monitor [risk or indicator], and sustain the work through [funding, partnership, policy, practice, or capacity plan].

# Commitments-to-results snapshot

| ID | Commitment | Indicator | Target | Actual | Status | Source |
| --- | --- | --- | --- | --- | --- | --- |
| [C-01] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |
| [C-02] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |
| [C-03] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |
| [C-04] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |
| [C-05] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |
| [C-06] | [Approved objective or commitment] | [Indicator / unit] | [Target] | [Actual] | [Status] | [Evidence source] |

# Progress against objectives

| Objective | [Approved objective and relevant commitment ID] |
| --- | --- |
| Planned approach | [Activities, partners, timing, and intended reach from the approved plan] |
| What occurred | [What was delivered, when, where, by whom, and at what scale] |
| Verified outputs | [Direct products with units and evidence sources] |
| Observed outcomes | [Change in knowledge, behavior, condition, access, policy, or system performance] |
| Variance | [Difference from plan, cause, consequence, and whether funder approval was required / received] |
| Learning and adaptation | [What the team learned and what changed as a result] |
| Next-period action | [Owner, date, dependency, and success signal] |

|  | Outcome language Activities describe the work. Outputs count direct products. Outcomes describe what changed. If evidence supports contribution rather than sole causation, say “contributed to” rather than “caused.” |
| --- | --- |

# Activities and reach

| Activity | When | Where | Who | Plan | Actual | Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| [Activity / service] | [Date / period] | [Location / channel] | [Audience] | [Planned reach] | [Actual reach] | [Quality / completion evidence] |
| [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |

# Outcome and evidence register

| ID | Outcome | Indicator | Base | Target | Actual | Source | Limit |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [O-01] | [Outcome statement] | [Indicator] | [Baseline] | [Target] | [Actual] | [Source / method] | [Limitation] |
| [O-02] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [O-03] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [O-04] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |

# Equity, access, and participant voice

Access: [Who participated, who did not, and which language, cost, technology, mobility, trust, timing, or eligibility barriers affected access].

Distribution of results: [Whether outcomes differed meaningfully across relevant groups or locations, using responsible and sufficiently aggregated data].

Participant or community voice: [Short verified insight or quotation, consent status, and why it matters to interpretation].

Adaptation: [What changed—or will change—to improve access, experience, or distribution of benefit].

# Challenges, changes, and risk response

| Issue | When | Effect | Response | Approval | Status |
| --- | --- | --- | --- | --- | --- |
| [Issue / change] | [When detected] | [Effect on scope, schedule, cost, quality, or results] | [Action and owner] | [Funder notice / approval] | [Current status] |
| [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [ ] | [ ] | [ ] | [ ] | [ ] | [ ] |

# Financial performance

| Category | Budget | Period | Cumulative | Balance | Var. | Explanation |
| --- | --- | --- | --- | --- | --- | --- |
| [Budget category] | [Approved] | [Current-period actual] | [Cumulative actual] | [Balance] | [Variance %] | [Explanation / approved change] |
| [Personnel] | [$ ] | [$ ] | [$ ] | [$ ] | [%] | [ ] |
| [Contracts] | [$ ] | [$ ] | [$ ] | [$ ] | [%] | [ ] |
| [Travel / program costs] | [$ ] | [$ ] | [$ ] | [$ ] | [%] | [ ] |
| [Indirect / administration] | [$ ] | [$ ] | [$ ] | [$ ] | [%] | [ ] |
| TOTAL | [$ ] | [$ ] | [$ ] | [$ ] | [%] | [Tie to finance records] |

Financial narrative: [Explain material underspending, overspending, timing differences, cost savings, match or leverage, reallocation, and any approval required. Confirm the figures reconcile to the organization’s accounting records.]

# Learning, sustainability, and next period

| What worked | [Evidence-backed practice, condition, partnership, or design choice to continue] |
| --- | --- |
| What did not work as expected | [Observation, evidence, and likely cause] |
| What changed | [Adaptation already made and the decision behind it] |
| Next-period priorities | [Top actions, owners, dates, and decision thresholds] |
| Sustainability | [Funding, staffing, partnership, policy, operational, or revenue path] |
| Unresolved risk | [Risk, likelihood, consequence, early warning, owner, and response] |
| Funder support requested | [Decision, connection, approval, technical assistance, or clarification needed] |

# Attachment and certification register

| Item | Rule | Owner | Date | Filename | Check |
| --- | --- | --- | --- | --- | --- |
| [Attachment] | [Required / optional] | [Owner] | [Version / date] | [File name] | [Verified] |
| [Financial report] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [Evaluation / data appendix] | [ ] | [ ] | [ ] | [ ] | [ ] |
| [Work sample / photo / story consent] | [ ] | [ ] | [ ] | [ ] | [ ] |

# Final review checklist

The report follows the funder’s current questions, order, limits, and certification language.

Every target and actual uses the same unit, period, population, and definition.

Numbers reconcile across the narrative, tables, attachments, prior reports, and accounting records.

Material variance is explained with cause, consequence, response, and approval status.

Stories and quotations have appropriate permission and contain no unnecessary identifying information.

The report distinguishes outputs, outcomes, estimates, and verified results.

Attachments open, use the required filenames, and contain no hidden comments or unintended data.

The program lead, finance lead, and authorized signer have completed their reviews.

Use note: This template is a general planning and communication resource. Follow the funder or issuer’s current instructions, portal fields, contract terms, certifications, and submission rules. Review material legal, financial, privacy, procurement, or compliance statements with the appropriate qualified professional.