## Instructions
GRANT TRACKING WORKBOOK
Manage the full grant lifecycle from prospect through decision, award, reporting, and closeout.
START HERE
1 | Enter each opportunity once in Pipeline and assign an owner, stage, fit score, deadline, request, and next action.
2 | Use Requirements for attachments, registrations, approvals, portal fields, and other submission dependencies.
3 | When an award is received, create one row per reporting or closeout obligation in Awards & Reporting.
4 | Keep contacts and communication preferences in Funder Contacts; avoid storing sensitive personal data not needed for the work.
5 | Review the Dashboard weekly and resolve overdue next actions, near-term deadlines, and open reporting obligations.
6 | Archive declined or closed opportunities by changing stage/status rather than deleting the record.
WORKBOOK CHECK
Active opportunities
Deadlines in next 30 days
Overdue next actions
Open requirements
Open reports
Legend
Input cells
Formula / reference cells
Example / optional prompts
Use note: This workbook supports planning and workflow management. Funder requirements, eligibility, deadlines, award terms, financial records, and reporting obligations must be verified against the current authoritative source. Do not use this workbook as the sole record of a legal, financial, or contractual obligation.

## Pipeline
GRANT PIPELINE
One row per opportunity. Use the next-action fields to keep the pipeline operational, not merely descriptive.
Opportunity ID | Funder | Program / opportunity | Opportunity URL | Opportunity type | Owner | Stage | Decision | Fit score (1–5) | Probability % | Request amount | Weighted pipeline | Project start | Project end | Deadline | Days to deadline | Next action | Next action due | Action alert | Last contact | Primary contact | Eligibility / fit note | Notes
| Example Community Fund | Resilient Neighborhoods 2027 | https://example.org/opportunity | Foundation | Development lead | Qualification | Pursue | 4 |  | 75000 |  | 2027-01-01 | 2027-12-31 | 2026-10-15 |  | Confirm eligibility call | 2026-09-10 |  | 2026-08-28 | [Name / role] | Strong mission and geography fit; verify indirect-cost cap. | Example only — replace with current source data.
Formulas:
Days to deadline = IF([Deadline]="","",[Deadline]-TODAY())
Action alert = IF(OR([Funder]="",[Next action due]=""),"",IF(OR([Stage]="Awarded",[Stage]="Declined",[Stage]="Closed"),"CLOSED",IF([Next action due]<TODAY(),"OVERDUE",IF([Next action due]<=TODAY()+7,"DUE SOON","ON TRACK"))))

## Requirements
REQUIREMENTS & SUBMISSION CHECKLIST
One row per requirement, attachment, approval, registration, portal field, or submission action.
Requirement ID | Opportunity ID | Category | Requirement / deliverable | Source / page | Required? | Owner | Status | Due date | Completed date | Evidence / file link | Reviewer note
| G-001 | Eligibility | Confirm indirect-cost cap and allowable base | Guidelines p. 8 | Yes | Finance lead | Not started | 2026-09-05 |  | [Link to source / evidence] | Example only.

## Awards & Reporting
AWARDS & REPORTING OBLIGATIONS
Create one row per report, payment request, certification, closeout, audit, or other award obligation.
Obligation ID | Opportunity ID | Funder | Award / agreement # | Award amount | Project start | Project end | Obligation type | Period covered | Due date | Status | Submitted date | Accepted date | Award spent to date | Award balance | Owner | File / portal link

## Funder Contacts
FUNDER CONTACTS
Funder | Contact name | Title / role | Email | Phone | Relationship owner | Contact preference / restriction | Last contact | Next contact | Notes

## Dashboard
GRANT PORTFOLIO DASHBOARD
Portfolio metric | Value | Stage | Count
Total opportunities |  | Prospect
Active opportunities |  | Researching
Total request pipeline |  | Qualification
Probability-weighted pipeline |  | LOI planned
Total awarded |  | LOI submitted
Submitted decisions |  | Invited
Awards |  | Application planned
Win rate |  | Application in progress
Deadlines next 30 days |  | Submitted
Overdue next actions |  | Decision pending
Open reporting obligations |  | Awarded
Declined
Closed