## Instructions
RISK ASSESSMENT & TREATMENT WORKBOOK
Document scope, scenarios, vulnerabilities, consequence, evidence, ownership, treatment, residual risk, and review.
WORKFLOW
1 | Define the decision, scope, risk horizon, stakeholders, method, rating anchors, and risk appetite in Method.
2 | List critical objectives, services, people, information, assets, obligations, and dependencies before identifying risks.
3 | Write each risk as a plausible cause/event and consequence; record the evidence, assumptions, and affected objective.
4 | Rate inherent likelihood and multi-dimensional impact before considering controls; document the rationale.
5 | Evaluate existing controls and evidence, then rate residual likelihood and impact rather than applying a hidden percentage reduction.
6 | Assign treatment, owner, due date, resources, target residual level, monitoring indicator, and review trigger; escalate beyond appetite.
WORKBOOK CHECK
Risks recorded
Critical / high residual
Beyond appetite
Overdue treatments
Risks missing evidence
Legend
Input
Formula / score
Example
Use note: This workbook supports structured management judgment and does not establish NIST, CISA, FEMA, ISO, insurance, audit, regulatory, safety, or legal conformance. Use authoritative hazard, incident, control, financial, operational, legal, and stakeholder evidence; involve qualified specialists for consequential risks.

## Method
ASSESSMENT METHOD
Assessment name | [Name / version]
Decision supported | [Prioritization, budget, project gate, control design, continuity, board oversight, or other]
Scope | [Organization, program, site, process, system, project, vendor, geography, or period]
Risk horizon | [Dates / near, medium, long term]
Assessment team | [Owner, subject experts, stakeholders, reviewers, facilitator]
Evidence cutoff | [Date and included sources]
Risk appetite / tolerance | [By objective/category and authority to accept]
Review cadence | [Monthly / quarterly / milestone / trigger]
Escalation route | [Who decides on critical/high or beyond-tolerance residual risk]
LIKELIHOOD ANCHORS
1 | Rare | Not expected in the stated horizon; strong evidence of low exposure.
2 | Unlikely | Plausible but not expected; limited precedent or exposure.
3 | Possible | Could occur; credible scenario or mixed evidence.
4 | Likely | Expected in many circumstances; recurring exposure or warning signs.
5 | Almost certain | Expected frequently or already occurring.
IMPACT ANCHORS
1 | Insignificant | Contained; minimal interruption, cost, harm, or reporting need.
2 | Minor | Manageable within routine authority and resources.
3 | Moderate | Material objective, service, cost, stakeholder, or compliance effect requiring coordinated response.
4 | Major | Severe effect, significant interruption or harm, executive action, or external notification.
5 | Catastrophic | Threatens life/safety, mission/viability, essential service, legal standing, or sustained recovery.
SCORING
Overall impact is the highest applicable impact dimension. Inherent score = inherent likelihood × inherent impact. Residual score = residual likelihood × residual impact after considering existing controls and evidence. Tiers: 1–4 Low; 5–9 Moderate; 10–16 High; 17–25 Critical. Rating anchors and escalation thresholds must be reviewed for the organization’s context.

## Objectives & Assets
OBJECTIVES, SERVICES, ASSETS & DEPENDENCIES
Record ID | Type | Objective / service / asset / obligation | Owner | Criticality (1–5) | Maximum tolerable disruption | Key dependencies | Minimum capability / safeguard | Evidence / source | Notes

## Risk Register
RISK REGISTER
Write risk as cause/event → consequence. Rate inherent risk before controls and residual risk after documented controls.
Risk ID | Category | Affected objective / asset | Risk statement | Threat / hazard / cause | Vulnerability / exposure | Evidence / source | Scenario / trigger | Risk owner | Inherent likelihood | People / safety impact | Mission / service impact | Financial impact | Legal / compliance impact | Data / technology impact | Reputation / stakeholder impact | Inherent impact | Inherent score | Inherent tier | Existing controls | Control evidence / effectiveness | Residual likelihood | Residual impact | Residual score | Residual tier | Appetite / tolerance | Escalation | Treatment choice | Review date | Notes
| Operational | OA-001 | If the primary file platform is unavailable for more than one business day, delivery teams may lose access to current client materials, causing missed commitments and privacy workarounds. | Cloud service outage or account compromise | Single production environment and uneven offline access | Vendor status history; internal incident log | Two-day outage during a deadline week | Operations lead | 3 | 1 | 4 | 3 | 3 | 4 | 4 |  |  |  | MFA, role-based access, local emergency copies for critical files, vendor support | Quarterly access review; last restore exercise [date] | 2 | 3 |  |  | Near limit |  | Reduce | 2026-10-31 | Example only — validate sources and ratings.

## Treatment Plan
RISK TREATMENT PLAN
Treatment ID | Risk ID | Treatment action | Control / deliverable | Owner | Approver | Start | Due | Resources / cost | Target residual score | Status | Schedule alert | Evidence / completion record | Validation test | Next review | Notes
Formulas:
Schedule alert = IF([Treatment action]="","",IF(OR([Status]="Complete",[Status]="Cancelled"),"CLOSED",IF([Due]="","NO DATE",IF([Due]<TODAY(),"OVERDUE",IF([Due]<=TODAY()+14,"DUE SOON","ON TRACK")))))

## Scenarios
THREAT / HAZARD SCENARIOS
Scenario ID | Scenario name | Threat / hazard | Time / place / conditions | Affected objectives / assets | Duration / scale | Early warning | Expected performance | Critical dependency failure | Decision / exercise use | Evidence / source | Owner | Review date

## Dashboard
RISK DASHBOARD
Metric | Value | Tier | Count
Risks |  | Critical
Critical residual |  | High
High residual |  | Moderate
Moderate residual |  | Low
Low residual
Beyond appetite
Open treatments
Overdue treatments
REFERENCE LINKS
NIST SP 800-30 Rev. 1 | https://csrc.nist.gov/pubs/sp/800/30/r1/final
CISA Risk Assessment Methodologies | https://www.cisa.gov/resources-tools/resources/risk-assessment-methodologies
FEMA Risk Management | https://www.fema.gov/emergency-managers/risk-management